## User Stories
EPIC | USER STORY | PRIORITY | VALUE | RISK | ESTIMATE | RELEASE | ACCEPTANCE | PRIORITY(INT) | VALUE(INT) | RISK(INT) | PRIORITY(INV) | VALUE(INV) | RISK(INV) | THEME(Sp) | FEATURE(Sp) | RELEASE(S) | ROW(S)
Login | As a USER, I want to be able to login, so that I can cast my votes | 1 High | 1 High | 1 High | SM | MVP | 1) the user can access a login form 2) field validation is required | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 0.0 MVP | 2
SignUp | As a USER, I want to be able to sign up, so that I can login to the platform | 1 High | 1 High | 1 High | SM | MVP | 1) the user can access a registration form 2) field validation is required | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 0.0 MVP | 3
Public Ballot Creation | As an USER, I want to be able to create a new ballot, so that the users can see it | 1 High | 1 High | 1 High | SM | MVP | 1) the admin can access a creation form | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 0.0 MVP | 4
Ballot Results | As a USER, I want to be able to see ballot results, so that I can I can understand the outcome of the voting process | 2 Med | 1 High | 2 Med | SM | MVP | 1) the users can access a dashboard | 2 | 1 | 2 | 3 | 4 | 3 |  |  | 0.0 MVP | 5
Ballot Voting | As a USER, I want to be able to cast a vote, so that I can contribute to the ballot | 1 High | 1 High | 1 High | LG | MVP | 1) the users can access a form to cast their vote | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 0.0 MVP | 6
Wallet Connection | As a USER, I want to be able to connect my wallet, so that I can cast my votes | 1 High | 1 High | 1 High | LG | MVP | 1) the user can | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 0.0 MVP | 7
Ballot List | As a USER, I want to be able to view all active ballots, so that I can choose one of my interest | 2 Med | 1 High | 3 Med | MD | MVP | 1) the user can access a dashboard | 2 | 1 | 3 | 3 | 4 | 2 |  |  | 0.0 MVP | 8
Profile Update | As a USER, I want to update my profile, so that I can keep my information up to date | 1 High | 2 Med | 2 Med | SM | 1.0 | 1) the user can access a form to update his information | 1 | 2 | 2 | 4 | 3 | 3 |  |  | 1.0 | 9
Friend Requests | As a USER, I want to be able to send friend requests, so that I can view my friends' interests | 3 Med | 2 Med | 4 Low | LG | 2.0 | 1) the user can search for other users | 3 | 2 | 4 | 2 | 3 | 1 |  |  | 2.0 | 10
Vote Confirmation | As a USER, I want to be notified that my vote was casted, so that I can be sure that my vote is counted | 2 Med | 2 Med | 4 Low | MD | 2.0 |  | 2 | 2 | 4 | 3 | 3 | 1 |  |  | 2.0 | 11
Ballots Bookmarking | As a USER, I want to be able to bookmark ballots, so that I can save them for later | 4 Low | 3 Med | 4 Low | SM | 2.x |  | 4 | 3 | 4 | 1 | 2 | 1 |  |  | 2.x | 12
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Value Pivot
THEME(Sp) | (più elementi)
RELEASE(S)
Totale complessivo
SUM of VALUE(INV)