## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | DB Creation | Lorenzo Gizzi | 4 | 4 | 0 | 1 |  |  |  | 100%
1.1 | DB design | Lorenzo Gizzi | 2 | 2 | 0 | 1 | 2024-07-03 | 2024-07-03 | 1 | 100% | bar: WEEK 1 W
1.2 | DB implementation | Lorenzo Gizzi | 2 | 2 | 0 | 1 | 2024-07-03 | 2024-07-03 | 1 | 100% | bar: WEEK 1 W
2 | SignUp Form Creation | Lorenzo Gizzi | 2 | 2 | 0 | 1 |  |  |  | 100%
2.1 | SignUp Page Creation | Lorenzo Gizzi | 2 | 2 | 0 | 1 | 2024-07-04 | 2024-07-04 | 1 | 100% | bar: WEEK 1 R
3 | SignUp Data Validation | Lorenzo Gizzi | 4 | 4 | 0 | 1 |  |  |  | 100%
3.1 | Validate the correctness of the user's data | Lorenzo Gizzi | 3 | 3 | 0 | 1 | 2024-07-08 | 2024-07-08 | 1 | 100%
3.2 | Send user's data to the server | Lorenzo Gizzi | 1 | 1 | 0 | 1 | 2024-07-08 | 2024-07-08 | 1 | 100%
4 | User's data insertion | Lorenzo Gizzi | 2 | 2 | 0 | 1 |  |  |  | 100%
4.1 | Update db | Lorenzo Gizzi | 2 | 2 | 0 | 1 | 2024-07-09 | 2024-07-09 | 1 | 100%
5 | Send Email | Lorenzo Gizzi | 4 | 4 | 0 | 1 |  |  |  | 100%
5.1 | API Credentials creation | Lorenzo Gizzi | 1 | 1 | 0 | 1 | 2024-07-09 | 2024-07-09 | 1 | 100%
5.2 | Body Message Creation | Lorenzo Gizzi | 1 | 1 | 0 | 1 | 2024-07-10 | 2024-07-10 | 1 | 100%
5.3 | Link the functionality to the signup button | Lorenzo Gizzi | 2 | 2 | 0 | 1 | 2024-07-10 | 2024-07-10 | 1 | 100%
6 | SignIn Form Creation | Lorenzo Gizzi | 2 | 2 | 0 | 1 |  |  |  | 100%
6.1 | SignIn Form Creation | Lorenzo Gizzi | 2 | 2 | 0 | 1 | 2024-07-11 | 2024-07-11 | 1 | 100%
7 | SignIn Data Validation | Lorenzo Gizzi | 4 | 4 | 0 | 1 |  |  |  | 100%
7.1 | Send user's data to the server | Lorenzo Gizzi | 1 | 1 | 0 | 1 | 2024-07-11 | 2024-07-11 | 1 | 100%
7.2 | Validate the correctness of the user's data | Lorenzo Gizzi | 2 | 2 | 0 | 1 | 2024-07-12 | 2024-07-12 | 1 | 100%
7.3 | Redirect the user to the homepage | Lorenzo Gizzi | 1 | 1 | 0 | 1 | 2024-07-12 | 2024-07-12 | 1 | 100%
8 | Board Creation | Lorenzo Russo | 8 | 8 | 0 | 2 |  |  |  | 100%
8,1 | Graphic board creation | Lorenzo Russo | 6 | 6 | 0 | 2 | 2024-07-15 | 2024-07-16 | 2 | 100% | bar: WEEK 2 M to WEEK 3 T
8.2 | Pawns and kings creation | Lorenzo Russo | 2 | 2 | 0 | 2 | 2024-07-16 | 2024-07-17 | 2 | 100% | bar: WEEK 3 T to WEEK 3 W
9 | Game Rules implementation | Lorenzo Russo | 24 | 24 | 0 | 2 |  |  |  | 100%
9,1 | Pawn rules creation | Lorenzo Russo | 1 | 1 | 0 | 2 | 2024-07-17 | 2024-07-17 | 1 | 100% | bar: WEEK 3 W
9,2 | King rules creation | Lorenzo Russo | 1 | 1 | 0 | 2 | 2024-07-18 | 2024-07-18 | 1 | 100% | bar: WEEK 3 R
9,3 | General game rules creation | Lorenzo Russo | 12 | 12 | 0 | 2 | 2024-07-18 | 2024-07-22 | 5 | 100% | bar: WEEK 3 R to WEEK 4 M
9,3,1 | Mandatory eat rule | Lorenzo Russo | 2 | 2 | 0 | 2 | 2024-07-23 | 2024-07-23 | 1 | 100% | bar: WEEK 4 T
9,3,2 | Best eat rule | Lorenzo Russo | 6 | 6 | 0 | 2 | 2024-07-24 | 2024-07-25 | 2 | 100% | bar: WEEK 4 W to WEEK 4 R
9,3,3 | Game end rule | Lorenzo Russo | 2 | 2 | 0 | 2 | 2024-07-25 | 2024-07-26 | 2 | 100% | bar: WEEK 4 R to WEEK 5 F
10 | Pawn Drag&Drop | Lorenzo Russo | 2 | 2 | 0 | 2 |  |  |  | 100%
10,1 | Pawn Drag&Drop | Lorenzo Russo | 2 | 2 | 0 | 2 | 2024-07-26 | 2024-07-26 | 1 | 100% | bar: WEEK 4 F to WEEK 5 F
11 | Matchmaking implementation | Lorenzo Russo | 4 | 4 | 0 | 2 |  |  |  | 100%
11,1 | Matchmaking rules | Lorenzo Russo | 3 | 3 | 0 | 2 | 2024-07-29 | 2024-07-29 | 1 | 100%
11,2 | Waiting room creation | Lorenzo Russo | 1 | 1 | 0 | 2 | 2024-07-29 | 2024-07-29 | 1 | 100%
12 | Moves exchange | Lorenzo Russo | 4 | 4 | 0 | 2 |  |  |  | 100%
12,1 | Send moves to server | Lorenzo Russo | 2 | 2 | 0 | 2 | 2024-07-30 | 2024-07-30 | 1 | 100%
12,2 | Server forwards the moves to the players | Lorenzo Russo | 1 | 1 | 0 | 2 | 2024-07-30 | 2024-07-30 | 1 | 100%
12,3 | Update board locally | Lorenzo Russo | 1 | 1 | 0 | 2 | 2024-07-30 | 2024-07-30 | 1 | 100%
13 | End Game handle | Lorenzo Russo | 4 | 4 | 0 | 2 |  |  |  | 100%
13,1 | Show the result on the screen | Lorenzo Russo | 2 | 2 | 0 | 2 | 2024-07-31 | 2024-07-31 | 1 | 100%
13,2 | Update the db with the result | Lorenzo Russo | 2 | 2 | 0 | 2 | 2024-07-31 | 2024-07-31 | 1 | 100%
14 | Withdraw implementation | Lorenzo Gizzi | 2 | 2 | 0 | 2 |  |  |  | 100%
14,1 | Add and configure the withdraw button | Lorenzo Gizzi | 1 | 1 | 0 | 2 | 2024-07-31 | 2024-07-31 | 1 | 100%
14,2 | Update the db with the result | Lorenzo Gizzi | 1 | 1 | 0 | 2 | 2024-07-31 | 2024-07-31 | 1 | 100%
15 | Account page creation | Lorenzo Russo | 2 | 2 | 0 | 3 |  |  |  | 100%
15,1 | Create account page | Lorenzo Russo | 1 | 1 | 0 | 3 | 2024-08-09 | 2024-08-09 | 1 | 100% | bar: WEEK 6 F
15,2 | Retrive data from DB | Lorenzo Russo | 1 | 1 | 0 | 3 | 2024-08-09 | 2024-08-09 | 1 | 100% | bar: WEEK 6 F
16 | Friend page creation | Lorenzo Gizzi | 2 | 2 | 0 | 3 |  |  |  | 100%
16,1 | Create friend page | Lorenzo Gizzi | 1 | 1 | 0 | 3 | 2024-08-09 | 2024-08-09 | 1 | 100% | bar: WEEK 6 F
16,2 | Retrive data from DB | Lorenzo Gizzi | 1 | 1 | 0 | 3 | 2024-08-09 | 2024-08-09 | 1 | 100% | bar: WEEK 6 F
17 | Player search | Lorenzo Russo | 4 | 4 | 0 | 3 |  |  |  | 100%
17,1 | Retrive data from DB | Lorenzo Russo | 2 | 2 | 0 | 3 | 2024-08-12 | 2024-08-12 | 1 | 100% | bar: WEEK 7 M
17,2 | Show the output on the friend page | Lorenzo Russo | 2 | 2 | 0 | 3 | 2024-08-12 | 2024-08-13 | 2 | 100% | bar: WEEK 7 M to WEEK 7 T
18 | Follow player | Lorenzo Russo | 2 | 2 | 0 | 3 |  |  |  | 100%
18,1 | Implement the follow feature | Lorenzo Russo | 2 | 2 | 0 | 3 | 2024-08-13 | 2024-08-13 | 1 | 100% | bar: WEEK 7 T
19 | Global champ creation | Lorenzo Gizzi | 2 | 2 | 0 | 3 |  |  |  | 100%
19,1 | Create graphic page | Lorenzo Gizzi | 1 | 1 | 0 | 3 | 2024-08-13 | 2024-08-13 | 1 | 100% | bar: WEEK 7 T
19,2 | Retrive data from DB | Lorenzo Gizzi | 1 | 1 | 0 | 3 | 2024-08-13 | 2024-08-13 | 1 | 100% | bar: WEEK 7 T
20 | Local champ creation | Lorenzo Gizzi | 2 | 2 | 0 | 3 |  |  |  | 100%
20,1 | Create graphic page | Lorenzo Gizzi | 1 | 1 | 0 | 3 | 2024-08-16 | 2024-08-16 | 1 | 100% | bar: WEEK 7 F to WEEK 8 F
20,2 | Retrive data from DB | Lorenzo Gizzi | 1 | 1 | 0 | 3 | 2024-08-16 | 2024-08-16 | 1 | 100% | bar: WEEK 7 F to WEEK 8 F
21 | Stats page creation | Lorenzo Russo | 2 | 2 | 0 | 3 |  |  |  | 100%
20,1 | Create graphic page | Lorenzo Russo | 1 | 1 | 0 | 3 | 2024-08-19 | 2024-08-19 | 1 | 100%
20,2 | Retrive data from DB | Lorenzo Russo | 1 | 1 | 0 | 3 | 2024-08-19 | 2024-08-19 | 1 | 100%
22 | Chat page creation | Lorenzo Gizzi | 2 | 2 | 0 | 4 |  |  |  | 100%
22,1 | Create graphic page | Lorenzo Gizzi | 2 | 2 | 0 | 4 | 2024-08-20 | 2024-08-20 | 1 | 100%
23 | Message exchange | Lorenzo Gizzi | 8 | 8 | 0 | 4 |  |  |  | 100%
23,1 | Rabbitmq configuration | Lorenzo Gizzi | 2 | 2 | 0 | 4 | 2024-08-20 | 2024-08-21 | 2 | 100%
23,2 | Handle the messages on the server | Lorenzo Gizzi | 4 | 4 | 0 | 4 | 2024-08-21 | 2024-08-22 | 2 | 100%
23,3 | Display the messages on the screens | Lorenzo Gizzi | 2 | 2 | 0 | 4 | 2024-08-23 | 2024-08-23 | 1 | 100%
24 | Message retrival | Lorenzo Gizzi | 4 | 4 | 0 | 4 |  |  |  | 100%
24,1 | Retrive messages from DB | Lorenzo Gizzi | 2 | 2 | 0 | 4 | 2024-08-26 | 2024-08-26 | 1 | 100% | bar: WEEK 8 M to WEEK 9 M
24,2 | Display the old messages on the screens | Lorenzo Gizzi | 2 | 2 | 0 | 4 | 2024-08-26 | 2024-08-26 | 1 | 100% | bar: WEEK 8 M to WEEK 9 M
25 | Friends game creation | Lorenzo Russo | 4 | 4 | 0 | 4 |  |  |  | 100%
25,1 | Implement the "challenge a friend" feature | Lorenzo Russo | 2 | 2 | 0 | 4 | 2024-08-26 | 2024-08-26 | 1 | 100% | bar: WEEK 8 M to WEEK 9 M
25,2 | Handle the game between friends | Lorenzo Russo | 2 | 2 | 0 | 4 | 2024-08-26 | 2024-08-26 | 1 | 100% | bar: WEEK 8 M to WEEK 9 M
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 104 | 104 | 0 | 55 | 1.8909 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 104 | 102.1091 | 100.2182 | 98.3273 | 96.4364 | 94.5455 | 92.6545 | 90.7636 | 88.8727 | 86.9818 | 85.0909 | 83.2 | 81.3091 | 79.4182 | 77.5273 | 75.6364 | 73.7455 | 71.8545 | 69.9636 | 68.0727 | 66.1818 | 64.2909 | 62.4 | 60.5091 | 58.6182 | 56.7273 | 54.8364 | 52.9455 | 51.0545 | 49.1636 | 47.2727 | 45.3818 | 43.4909 | 41.6 | 39.7091 | 37.8182 | 35.9273 | 34.0364 | 32.1455 | 30.2545 | 28.3636 | 26.4727 | 24.5818 | 22.6909 | 20.8 | 18.9091 | 17.0182 | 15.1273 | 13.2364 | 11.3455 | 9.4545 | 7.5636 | 5.6727 | 3.7818 | 1.8909 | 1.3767e-14 | -1.8909 | -3.7818 | -5.6727 | -7.5636
[10 empty] | ESTIMATE | 104 | 100 | 98 | 98 | 98 | 98 | 94 | 91 | 88 | 85 | 82 | 82 | 82 | 79 | 75 | 73 | 71 | 68 | 65 | 63 | 62 | 58 | 55 | 51 | 48 | 48 | 48 | 44 | 40 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 30 | 30 | 30 | 27 | 22 | 22 | 22 | 20 | 20 | 20 | 18 | 15 | 12 | 10 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 2776
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 4 | 2 | 0 | 0 | 0 | 4 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 4 | 2 | 2 | 3 | 3 | 2 | 1 | 4 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 5 | 0 | 0 | 2 | 0 | 0 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 8 | [5 empty] | 104
[10 empty] | HRS REMAINING | 100 | 98 | 98 | 98 | 98 | 94 | 91 | 88 | 85 | 82 | 82 | 82 | 79 | 75 | 73 | 71 | 68 | 65 | 63 | 62 | 58 | 55 | 51 | 48 | 48 | 48 | 44 | 40 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 30 | 30 | 30 | 27 | 22 | 22 | 22 | 20 | 20 | 20 | 18 | 15 | 12 | 10 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2672
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
H | 1 | DB | DB Creation | create the DB by following the ER diagram | Lorenzo Gizzi | 4 | Completed |  | Not Started | 1
H | 1 | SignUp | SignUp form creation | create the view for the sign up phase | Lorenzo Gizzi | 2 | Completed |  | In Progress | 2
H | 1 | SignUp | SignUp Data Validation | validate the correctness of the user's data | Lorenzo Gizzi | 4 | Completed |  | Completed | 4
H | 1 | SignUp | User's data insertion | insert user's data in the DB once validated | Lorenzo Gizzi | 2 | Completed |  |  | 8
M | 1 | SignUp | Send Mail | send email message for successful registration | Lorenzo Gizzi | 4 | Completed |  |  | 16
H | 1 | SignIn | SignIn form creation | create the view for the sign in phase | Lorenzo Gizzi | 2 | Completed |  |  | 24
H | 1 | SignIn | SignIn Data Validation | validate the correctness of the user's data | Lorenzo Gizzi | 4 | Completed |  |  | 40
H | 2 | Game | Board creation | create the game environment | Lorenzo Russo | 8 | Completed |  |  | 80
H | 2 | Game | Game Rules implementation | implement the Dama rules | Lorenzo Russo | 24 | Completed
H | 2 | Game | Pawn Drag&Drop | implement the drag and drop for the pawns and the kings | Lorenzo Russo | 2 | Completed
H | 2 | Game | Matchmaking implementation | implement the matchmaking phase to match players with similar elo | Lorenzo Russo | 4 | Completed
H | 2 | Game | Moves exchange | implement the exchange of the moves between the two players | Lorenzo Russo | 4 | Completed
H | 2 | Game | End Game handle | handle the end of a game by augmenting the elo and the level of the winner and save the game in the db | Lorenzo Russo | 4 | Completed
L | 2 | Game | Withdraw implementation | handle the possibility to withdraw from a match | Lorenzo Gizzi | 2 | Completed
H | 3 | User infos | Account Page creation | create the account page view to show personal infos | Lorenzo Russo | 2 | Completed
H | 3 | Friendship | Friends Page creation | create the friends page view | Lorenzo Gizzi | 2 | Completed
H | 3 | Friendship | Player Search | implement the search of a player according to the username inserted in the searchbar | Lorenzo Russo | 4 | Completed
H | 3 | Friendship | Follow Player | implement the possibility to follow players | Lorenzo Russo | 2 | Completed
M | 4 | Messaging | Chat Page creation | create the chat page view | Lorenzo Gizzi | 2 | Completed
M | 4 | Messaging | Message exchange | create the mechanism to exhange messages among friends | Lorenzo Gizzi | 8 | Completed
M | 4 | Messaging | Message retrival | retrieve the old messages among two users | Lorenzo Gizzi | 4 | Completed
H | 4 | Game | Friends Game creation | implement the game among friends | Lorenzo Russo | 4 | Completed
L | 3 | Game Infos | Global Champ creation | create a page showing the global champ | Lorenzo Gizzi | 2 | Completed
L | 3 | Game Infos | Local Champ creation | create a page showing the championship table among friends | Lorenzo Gizzi | 2 | Completed
L | 3 | Game Infos | Stats Page creation | create a page showing the statistics of an user | Lorenzo Russo | 2 | Completed

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
DB Creation | create the DB by following the ER diagram | Lorenzo Gizzi | 2024-07-03
SignUp form creation | create the view for the sign up phase | Lorenzo Gizzi | 2024-07-03
SignUp Data Validation | validate the correctness of the user's data | Lorenzo Gizzi | 2024-07-03
User's data insertion | insert user's data in the DB once validated | Lorenzo Gizzi | 2024-07-03
Send Mail | send email message for successful registration | Lorenzo Gizzi | 2024-07-03
SignIn form creation | create the view for the sign in phase | Lorenzo Gizzi | 2024-07-03
SignIn Data Validation | validate the correctness of the user's data | Lorenzo Gizzi | 2024-07-03
Board creation | create the game environment | Lorenzo Russo | 2024-07-08
Game Rules implementation | implement the Dama rules | Lorenzo Russo | 2024-07-08
Pawn Drag&Drop | implement the drag and drop for the pawns and the kings | Lorenzo Russo | 2024-07-08
Matchmaking implementation | implement the matchmaking phase to match players with similar elo | Lorenzo Russo | 2024-07-08
Moves exchange | implement the exchange of the moves between the two players | Lorenzo Russo | 2024-07-08
End Game handle | handle the end of a game by augmenting the elo and the level of the winner and save the game in the db | Lorenzo Russo | 2024-07-08
Withdraw implementation | handle the possibility to withdraw from a match | Lorenzo Gizzi | 2024-07-08
Account Page creation | create the account page view to show personal infos | Lorenzo Russo | 2024-07-23
Friends Page creation | create the friends page view | Lorenzo Gizzi | 2024-07-23
Player Search | implement the search of a player according to the username inserted in the searchbar | Lorenzo Russo | 2024-07-23
Follow Player | implement the possibility to follow players | Lorenzo Russo | 2024-07-23
Chat Page creation | create the chat page view | Lorenzo Gizzi | 2024-07-29
Message exchange | create the mechanism to exhange messages among friends | Lorenzo Gizzi | 2024-07-29
Message retrival | retrieve the old messages among two users | Lorenzo Gizzi | 2024-07-29
Friends Game creation | implement the game among friends | Lorenzo Russo | 2024-08-19
Global Champ creation | create a page showing the global champ | Lorenzo Gizzi | 2024-08-19
Local Champ creation | create a page showing the championship table among friends | Lorenzo Gizzi | 2024-08-19
Stats Page creation | create a page showing the statistics of an user | Lorenzo Russo | 2024-08-19